## Sheet1
Task ID | Task Name | Owner | Start Week | End Week | Week 1 | Week 2 | Week 3 | Week 4 | Week 5
1 | Project Kickoff & Role Assignment | Trevor | Week 1 | Week 1
2 | Software Requirements Specification (SRS) | Trevor | Week 1 | Week 1
3 | Requirements Review & Validation | Michael, Dontae | Week 1 | Week 1
4 | Gantt Chart Creation | Trevor | Week 2 | Week 2
5 | Task Breakdown & Estimation | Dontae | Week 2 | Week 2
6 | Wireframe Design | Michael | Week 2 | Week 2
7 | Design Review & Adjustments | Trevor | Week 2 | Week 2
8 | Core React Navigation & Routing | Trevor | Week 3 | Week 3
9 | StreamList CRUD Functionality | Trevor | Week 3 | Week 3
10 | UI Styling Enhancements | Michael | Week 3 | Week 3
11 | Requirements Compliance Review | Dontae | Week 3 | Week 3
12 | Movies Page Implementation | Trevor | Week 4 | Week 4
13 | Cart Page Implementation | Trevor | Week 4 | Week 4
14 | Wireframe Updates (If Needed) | Michael | Week 4 | Week 4
15 | Feature Verification & Feedback | Dontae | Week 4 | Week 4
16 | About Page Implementation | Trevor | Week 5 | Week 5
17 | Security & Ethics Documentation | Trevor | Week 5 | Week 5
18 | Final UI Review | Michael | Week 5 | Week 5
19 | Final Requirements Validation | Dontae | Week 5 | Week 5
20 | Final Presentation & Submission | Trevor | Week 5 | Week 5